BREATHE

2-Week Prototype Build Plan — Team of 2

# Remaining Work, By Priority

- 1. NHANES classifier — train and wire into the PHRS engine (blocks calibration and final scoring).

- 2. PHRS calibration — tune formula weights against published Delhi/Varanasi risk data.

- 3. ESP32 hardware — flash real sensor node, wire to /ingest, set up simulated nodes for IDW.

- 4. Fitbit integration — backend polling into /vitals, biometric risk modifier.

- 5. Frontend — minimal live score + map display.

- 6. Full integration + demo rehearsal.

Two tracks run in parallel throughout: Backend/ML (items 1, 2, 4) and Hardware/Delivery (items 3, 5). They converge for item 6 in the final days.

# Week 1 — Build the Core

## Days 1–2

| Backend / ML track | Hardware / Delivery track |
| --- | --- |
| Confirm NHANES files downloaded; join + clean data; begin classifier training | Register Fitbit developer app; confirm OAuth working |
|  | Gather ESP32 + PMS5003 + DHT22; test wiring on breadboard |

Checkpoint: NHANES data ready for training. Fitbit auth confirmed working.

## Days 3–4

| Backend / ML track | Hardware / Delivery track |
| --- | --- |
| Finish training NHANES classifier; evaluate output quality | Flash ESP32 with sensor code; confirm it posts readings to /ingest |
| Pull published Delhi/Varanasi risk numbers; run calibration test cases | Set up 2-3 simulated sensor nodes for the IDW demo mesh |

Checkpoint: classifier trained and sanity-checked. One real sensor sending live data to the backend.

## Days 5–7

| Backend / ML track | Hardware / Delivery track |
| --- | --- |
| Wire NHANES classifier output into the PHRS engine, replacing the hardcoded condition-weight table | Test IDW output with real + simulated nodes across a few locations; confirm sane blending |
| Adjust PHRS weights based on calibration results | Start minimal frontend: live score display + simple map view |

End of Week 1 milestone: full backend pipeline (sensors → IDW → PHRS with real classifier) working end-to-end via API calls, even without the watch or final frontend.

# Week 2 — Integrate, Polish, Rehearse

## Days 8–9

| Backend / ML track | Hardware / Delivery track |
| --- | --- |
| Implement Fitbit polling → /vitals; test biometric risk modifier with real watch data | Continue frontend build: connect it to live /predict and /ingest data |
| Retrain or re-source AQI Forecaster training data if time allows | Finalize physical sensor placement/spacing for the demo mesh |

## Days 10–11

Both tracks converge

Full end-to-end integration: real sensor + simulated nodes + real watch + frontend, all talking to the live backend

Fix integration bugs as they surface; re-run calibration checks after any formula changes

Checkpoint: a person can walk up, the app reads their profile + live watch + live sensors, and shows a real score on the frontend.

## Days 12–13

Both tracks converge

Prepare a scripted demo scenario and a fallback (pre-recorded/mock data) in case live hardware misbehaves

Polish frontend visuals; write a short one-page project summary for presentation

Full dry run of the demo, timed

## Day 14

Both tracks converge

Buffer day — fix whatever broke in the dry run; final rehearsal

# Things That Can Slip Without Breaking the Demo

- Full AQI Forecaster retraining — if time runs short, the demo can show current-conditions PHRS without the forecast trend.

- Real Health Connect/HealthKit integration — Fitbit Web API polling is sufficient for the prototype; native integration is a clearly-labeled future step.

- 5-node hardware mesh — 1 real node + simulated nodes proves the architecture; more physical nodes are a post-prototype upgrade.